## Sheet1
nfcpower10
rev2 changes
2021-01-23
Item | Change | Reason | Date Requested | Date Complete
1 | Change U3 SI5351A voltages VDD and VDDO to 3.3V | SI5351A has a maximum operating voltage of 3.6V which is not tolerant of the 5V configuration in rev1 | 2021-01-23 | 2021-01-23
2 | Add 5V to 3.3V level shifters to U3 SCL and SDA | Level shift the I2C signal for SI5351A | 2021-01-23 | 2021-01-23
3 | Use U2 FT231 3V3OUT for 3.3V rail and add 10uF bulk to this rail for stability | Utilize the existing 3.3V regulator from FT231 for operating SI5351A | 2021-01-23 | 2021-01-23
4 | Add TEMD7000X01 photodiodes and low pass filters | Light sensors - Cancel LSEN1 because it interferes with location of in-plane field sensor. Just use the offset light sensor. | 2021-01-23 | Cancel | 1e-09 | 1000000 | 0.001 | 159.1549
5 | Add VL6180X proximity and edge detectors | Board-Web parallelism and lamp alignment trigger | 2021-01-23 | 2021-01-23
6 | Add hardware I2C addresses to transmitters | Eliminate UART address assignment | 2021-01-23 | 2021-01-23
7 | Move transmitter coil closer to board edge and place mechanical header inside coil. | Increase line of site to lamp for camera when transmitter coil is aligned with the lamp antenna | 2021-01-23 | 2021-01-24
8 | Remov R6 and change R7 to 100nF | Use a cap on DTR to trigger reset from USB after programming | 2021-01-23 | 2021-01-23
9 | Connect U3 SI5351A OEB and SSEN to GND | Enable clock outputs by permanently and disable spread spectrum | 2021-01-23 | 2021-01-23
10 | Change R11 and R12 to 1.65kOhm | Increase I2C pull down current for faster bus speed | 2021-01-23 | 2021-01-23
11 | Remove host TX/RX from transmitters instead change to TXT and RXT on separate pins | Allow USB serial to communicate with the host on TX/RX | 2021-01-23 | 2021-01-23 | 1e-08 | 5000 | 5e-05 | 3183.0989
12 | Change transmitter HSEN2 divider to 1.65kOhm by 10kOhm | The offset field sensor has lower value so don't divide by 2 like HSEN1 | 2021-01-23 | 2021-01-23 | 1e-08 | 1000 | 1e-05 | 15915.4943
13 | Change HSEN1 cap filter to 220nF | 1ms time constant to filter field signal | 2021-01-23 | 2021-01-23 | 2.2e-07 | 5000 | 0.0011 | 144.6863
14 | Change HESEN2 cap filter to 1uF | 1ms time constant to filter field signal | 2021-01-23 | 2021-01-23 | 1e-06 | 1650 | 0.00165 | 96.4575
15 | Add 4 pin socket for 3.3V I2C for global trigger | Global trigger for side of web | 2021-01-23 | 2021-01-23
16 | Add 4 pin socket for quadrature encoder | Encoder for web speed and displacement | 2021-01-23 | 2021-01-23
17 | Update offset field sensor, board edge, add photodiodes, 4 pin header, move mechanical header inside coil | Offset Light Sensor LSEN2 reverse bias TEMD7000X01 into 1MOhm with parallel 1nF |  |  | 315.5 | 82 | 0 | 326 | 96 | -90